## ListOfFeatures
Product Backlog - Project Title (List of your features)
User Stories / List of features
As a user I am able to seemly search, find, buy and also recommend products.
As a user I am able to search products by categories, brand, model, and year
As a user I am able to sort my product search result by price and year (asc & desc).
As a site visitor, I have the possibility to compare prices for different packages and select the one that is suitable for me.
As an online buyer, I should be able to give feedback on the product that I have bought
As a site visitor, I am able to subscribe to newsletters to remain upto date on the newer products
Add, update, remove products to/from shopping card..
Register & login ->Crud -> user profile (personal info).
Crud favorite AND OR wish product lists
View my order or purchase histry
Maybe in future -> also sell products I bought from this site as a b-stock, given it still in very good condition

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | Deadline | STATUS
User Story/ Feature #1
Task : Create database | 2 | Onni | 11.02.2022 | Done
Task : Create demodata | 2 | Ilyass | not strict | Done
Task: Back-end - Get front-end to make db_requset, pass results back to front-end | 3 | Tim | 11.02.2022 | Done
User Story #2
Task Planning the website |  | Ilyass, Onni, Tim | No deadline | Done
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dummy data, icons, or images too. database tables are based on this
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bootstrap, define rows & columns for desktop, tablets, and mobile... Remenber icons
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: You need: 1- database defined and done... 2- Frontend defined ad done...
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | Deadline
User Story #1
Task : Make a list of categories, subcategories, products, table + data AND Universal nav | 2 | Onni | Done | 16.02.2022
Task : Make main page, + Single product page, Shopping cart. | 2 | Ilyass | Done | 18.02.2022
Task : Retrieve data by search, category select and display in respective page | 4 | Tim | Done | 18.02.2022
Task: | 2
User Story #2
Task : demodata |  | Ilyass, Onni, Tim |  | No dealine
Task: Log in/Registration page for customers/Employees + reset password | 2 | Onni | Done | 18.02.2022
Task : Insert demo data to the website | 2 | ilyass | Done | 18.02.2022
Task : User profile/Employee profile | 2 | ilyass | Moved to next sprint -> | 18.02.2022
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | Deadline
User Story #1
Task : User profile/Employee profile | 2 | ilyass | Done | 18.02.2022
Task: Everything to do with the products | 4 | Tim | Ongoing
User Story #2
Task: Checkout |  | Tim | Done | 25.02.2022
Task : demodata |  | Ilyass, Onni, Tim | Done | No dealine
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.

## sprint4
Sprint Backlog : Sprint 3 (Feb 28 - Mar 3)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | Deadline
User Story #1
Task: Testing |  | Ilyass, Onni, Tim | Done | 03.03.2022
Task: Data fitting |  | Ilyass, Onni, Tim | Done | 03.03.2022
Task: Feedback |  | Ilyass, Onni, Tim | Done | 03.03.2022
Task: Uploading to shell.hamk server |  | Tim | Done | 03.03.2022
User Story #2
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL